## PROJECT INFO
ASPEN
Phase I - ecs.py Module
Project Start Date | Project End Date
26/12/2016 | Assigned Resource: | Jogesh and Sachin

## INSTANCE INTERFACES
ECS -Create Instance - Business Scenario
Test Case Id | Test Case Name | Playbook File | Description | Expected Result | Actaul Result | Click2Cloud - Status | Aliyun - Status
1 | Verify that instance is not creating with unsubcribed image id | CreateAnInstanceWithUnsubscribedImageId.yml | In this Playbook , we tried to provide unsubscribed image id to create an ecs instance | ECS Instance should not be created with unsubscribed Image id | ECS Instance is not created when user provides unsubscribed image id | Pass
2 | Verify that instance is not creating with invalid instant type | launchAnInstanceWithInvalidInstantType.yml | In this Playbook , we tried to provide invalid Instant type to create an ecs instance | ECS Instance should not be created with invalid Instant type | ECS Instance is not created when user provides iinvalid Instant type | Pass
3 | Verify that instance is creating with defined tags | launchInstanceWithTagging.yml | In this Playbook , we tried to provide valid tags for ECS instance | ECS Instance should be created with defined tags | ECS Instance is created with defined tags | Pass
4 | Verify that Instance is creating and Elastic IP is assgined to it | CreateInstanceAndAssignEipToIt.yml | In this Playbook , we tried to create to ECS instance and assigned Elastic Ip to it | ECS Instance should be created and EIP should be assigned to it | ECS Instance is created and EIP is asigned to it | Pass
5 | Verify that VPC is not assigning to the instance which is created in different Region | CreateInstanceInDifferentRegionAsWithTheAssiginingVPCRegion.yml | In this Playbook , we tried to assign VPC to the instance which is created in different Region | VPC should not be assigned to the instance which is created in different region | VPC is not assigned to the instance which is created in different region | Pass
6 | Verify that user is unable to add more than 4 volumes to the ECS instance | CreateInstanceWithMoreThan4Volumes.yml | In this Playbook , we tried to assign more than 4 volumes to the instance | more than 4 volumes should not be added to ECS instance. | User is unable to add more than 4 volumes to the ECS Instance | Pass
7 | Verify that number of instances is created based on the count parameter value (e.g. Count = 2 , Instance created = 2 ) | CreateInstanceWithValidCountParameter.yml | In this Playbook , we tried to provide count parameter with value :2 | 2 instances should be created | 2 instances is created successfully | Pass
Adding an Instance to a Security Group
Test Case Id | Test Case Name | Playbook File | Description | Expected Result | Actaul Result | Click2Cloud - Status | Aliyun - Status
1 | Verify that user is able to add 2 instances to the defined Security Group | Add2InstancesToSecurityGroup.yml | In these playbooks , we tried to cover all parameter validation and Basic Scenarios for adding Instance to the security group | 2 different instances should be added to security Group successfully | 2 different instances is added to security Group successfully | Pass
2 | Verify that user is unable to add instance to the defined Security Group with parameter State- Absent and SG_Action - join | addInstanceToSecGroupWithParamState_Absent_SG_Action_Join.yml | In these playbooks , we tried to cover all parameter validation and Basic Scenarios for adding Instance to the security group | Instance should not be added to security Group if user provides the parameter State- Absent and SG_Action - join | Instance is not added to security Group if user provides the parameter State- Absent and SG_Action - join | Pass
3 | Verify that user is unable to add invalid Secuirity Group to the Valid Instance | addInvalidSecGroupToExistingInstance.yml | In these playbooks , we tried to cover all parameter validation and Basic Scenarios for adding Instance to the security group | instance should not be added to invalid security Group | instance is not added to invalid security Group | Pass
4 | Verify that user is unable to add invalid Secuirity Group to the invalid Instance | addInvalidSecGroupToInvalidInstance.yml | In these playbooks , we tried to cover all parameter validation and Basic Scenarios for adding Instance to the security group | invalid instance should not be added to invalid security Group . | invalid instance is not added to invalid security Group . | Pass
5 | Verify that user is able to add Secuirity Group to the ECS Instance | addSecGroupToExistingInstance.yml | In these playbooks , we tried to cover all parameter validation and Basic Scenarios for adding Instance to the security group | instance should be added to security Group | instance is added to security Group successfully | Pass
6 | Verify that user is unable to add Secuirity Group to the invalid Instance | addSecGroupToInvalidInstance.yml | In these playbooks , we tried to cover all parameter validation and Basic Scenarios for adding Instance to the security group | Invalid instance should not be added to valid security Group | Invalid instance is not added to valid security Group | Pass
7 | Verify that user is able to create ECS Instance With Defined Security Group | createAnECSInstanceWithDefinedSecGroup.yml | In these playbooks , we tried to cover all parameter validation and Basic Scenarios for adding Instance to the security group | ECS instance should be created with Defined Security Group successfully | ECS instance is created with Defined Security Group successfully | Pass
8 | Verify that user is able to create ECS Instance and then adding Security Group to it in different task. | CreateECSInstanceNAddIToSecurityGroup.yml | In these playbooks , we tried to cover all parameter validation and Basic Scenarios for adding Instance to the security group | ECS instance should be created and then Instance should be added to Security Group in different task | ECS instance is created and then Instance also added to Security Group in different task | Pass
9 | Verify that user is able to get incorrect instance status | IncorrectInstanceStatus.yml | In these playbooks , we tried to cover all parameter validation and Basic Scenarios for adding Instance to the security group | Difficult to generate this scenario, accidently , we tested this scenario 2 3 times, and it is working as expected | accidently , we tested this scenario 2 3 times, and it is working as expected | Pass
10 | Verify that user is unable to add VPC Instance to the VPC Security Group which belongs to the different VPCs | instanceAndSecurityGroupNotInSameVPC.yml | In these playbooks , we tried to cover all parameter validation and Basic Scenarios for adding Instance to the security group | VPC instance should not be added to the VPC Security Group if it belongs to the different VPC | VPC instance is not added to the VPC Security Group if it belongs to the different VPC | Pass
11 | Verify that user is unable add Instance to the security Group id if instance already exist in that Security Group . | InstanceIdAlreadyExists.yml | In these playbooks , we tried to cover all parameter validation and Basic Scenarios for adding Instance to the security group | instance should not be added to the Security Group if instance already exist in that Security Group . | instance is not added to the Security Group if instance already exist in that Security Group . | Pass
12 | Verify that user is unable to add VPC instance to CLASSIC Security Group | InstanceInVPCSecGroupInClassic.yml | In these playbooks , we tried to cover all parameter validation and Basic Scenarios for adding Instance to the security group | VPC instance should not be added to the CLASSIC Security Group | VPC instance is not added to the CLASSIC Security Group | Pass
13 | Verify that user is unable to add more than 5 security groups to the 1 instance | InstanceSecurityGroupLimitExceeded.yml | In these playbooks , we tried to cover all parameter validation and Basic Scenarios for adding Instance to the security group | one Instance should not be added to more than 5 security Groups | one Instance is not added to more than 5 security Groups | Pass
14 | Verify that user is unable to add Security Group to the instance if he/she missed to provide Instance Id | missingParameter_InstanceId.yml | In these playbooks , we tried to cover all parameter validation and Basic Scenarios for adding Instance to the security group | Instance should not be added to security Group if he/she missed to provide Instance Id | Instance is not added to security Group if he/she missed to provide Instance Id | Pass
15 | Verify that user is unable to add Security Group to the instance if he/she missed to provide Security Group Id | missingParameter_SecurityGroupId.yml | In these playbooks , we tried to cover all parameter validation and Basic Scenarios for adding Instance to the security group | Instance should not be added to security Group if he/she missed to provide Security Group Id | Instance is not added to security Group if he/she missed to provide Security Group Id | Pass
16 | Verify that user is able to add Security Group to the if both are in VPC | SecGroupAndECSInstanceBothInVPC.yml | In these playbooks , we tried to cover all parameter validation and Basic Scenarios for adding Instance to the security group | Instance should be added to Security Group if both are in VPC | Instance is added to Security Group if both are in VPC | Pass
17 | Verify that user is unable to add CLASSIC instance to VPC Security Group | SecGroupInVPCInstanceInClassic.yml | In these playbooks , we tried to cover all parameter validation and Basic Scenarios for adding Instance to the security group | Classic instance should not be added the VPC Security Group | Classic instance is not added the VPC Security Group | Pass
18 | Verify that user is unable to add more than 1000 instances to the 1 security group | SecurityGroupInstanceLimitExceeded.yml | In these playbooks , we tried to cover all parameter validation and Basic Scenarios for adding Instance to the security group | more than 1000 instances should not be added to the 1 security Group | more than 1000 instances is not added to the 1 security Group | Pass
Removing an Instance from a Security Group
Test Case Id | Test Case Name | Playbook File | Description | Expected Result | Actaul Result | Click2Cloud - Status | Aliyun - Status
1 | Verify that user is unable to remove Secuirity Group from the invalid ECS Instance | RemoveSecGroupFromInvalidInstance.yml | In these playbooks , we tried to cover all parameter validation and Basic Scenarios for removing Instance from the security group | Security Group should not be removed from the invalid Security Group | Security Group is not removed from the invalid Security Group | Pass
2 | Verify that user is able to remove Secuirity Group from the ECS Instance | RemoveSecGroupFromExistingInstance.yml | In these playbooks , we tried to cover all parameter validation and Basic Scenarios for removing Instance from the security group | Security Group should be removed from the Valid ECS Instance | Security Group is not removed from the Valid ECS Instance | Pass
3 | Verify that user is unable to remove invalid Secuirity Group from the invalid ECS Instance | RemoveInvalidSecGroupFromInvalidInstance.yml | In these playbooks , we tried to cover all parameter validation and Basic Scenarios for removing Instance from the security group | Invalid Security Group should not be removed from the Invalid ECS Instance | Invalid Security Group is not removed from the Invalid ECS Instance | Pass
4 | Verify that user is unable to remove invalid Secuirity Group from the ECS Instance | RemoveInvalidSecGroupFromExistingInstance.yml | In these playbooks , we tried to cover all parameter validation and Basic Scenarios for removing Instance from the security group | Invalid Security Group should not be removed from the ECS Instance | Invalid Security Group is not removed from the ECS Instance | Pass
5 | Verify that user is unable to remove Security Group from the instance if he/she missed to provide Security Group Id | missingParameter_SecurityGroupId.yml | In these playbooks , we tried to cover all parameter validation and Basic Scenarios for removing Instance from the security group | Instance should not be removed from security Group if he/she missed to provide security group id | Instance is not removed from security Group if he/she missed to provide security group id | Pass
6 | Verify that user is unable to remove Security Group from the instance if he/she missed to provide Instance Id | missingParameter_InstanceId.yml | In these playbooks , we tried to cover all parameter validation and Basic Scenarios for removing Instance from the security group | Instance should not be removed from security Group if he/she missed to provide Instance Id | Instance is not removed from security Group if he/she missed to provide Instance Id | Pass
7 | Verify that user is unable to remove last Security Group from the instance as instance must belong to the atleast 1 security Group | InstanceLastSecurityGroup.yml | In these playbooks , we tried to cover all parameter validation and Basic Scenarios for removing Instance from the security group | Instance should not be removed from security Group if instance belongs to the only 1 security Group | Instance is not removed from security Group if instance belongs to the only 1 security Group | Pass
8 | Verify that user is able to get incorrect instance status | IncorrectInstanceStatus.yml | In these playbooks , we tried to cover all parameter validation and Basic Scenarios for removing Instance from the security group | Difficult to generate this scenario, accidently , we tested this scenario 2 3 times, and it is working as expected |  | Pass
Querying an Instance Status
Test Case Id | Test Case Name | Playbook File | Description | Expected Result | Actual Result | Click2Cloud Testing Team | Aliyun Testing Team
1 | Verify that an instance is queried when Alias are provided for region and zone | query_instance_status_AcsRegionAcsZoneParameter.yml | In this Playbook, we tried to query an instance status with Alias as Acs Region and Acs Zone parameter | Instance status should be queried | Instance status is queried successfully | Pass
2 | Verify that an instance is not queried when valid region and invalid zone is provided | query_instance_status_WithValidRegionAndInvalidZoneParameter.yml | In this Playbook, we tried to query an instance status with valid region and invalid zone parameter which is invalid test case | Instance status should be queried | Instance status is queried successfully | Pass
3 | Verify that an instance is queried when Alias is provided for zone parameter | query_instance_status_ZoneParameterAlias.yml | In this Playbook, we tried to query an instance status with Alias as Zone | Instance status should be queried | Instance status is queried successfully | Pass
4 | Verify that an instance is queried when Alias is provided as Status | query_instance_statusWithAliasAsStatus.yml | In this Playbook, we tried to query an instance status with Alias as Status | Instance status should be queried | Instance status is queried successfully | Pass
5 | Verify that an instance is queried when Alias are provided for Access key, Secret key and other parameters | query_instance_statusWithAliaseAsAccessKeySecretKeyAndOthers.yml | In this Playbook, we tried to query an instance status with Alias as AccessKey, SecretKey and other parameter | Instance status should be queried | Instance status is queried successfully | Pass
6 | Verify that an instance is queried with Default pagesize and pagenumber parameter | query_instance_statusWithDefaultPageSizeAndPageNumberParameter.yml | In this Playbook, we tried to query an instance status with Default page size and page number parameter | Instance status should be queried | Instance status is queried successfully | Pass
7 | Verify that an instance is queried with Alias as Ecs AccessKey Ecs SecretKey and other parameters | query_instance_statusWithEcsAliaseAsAccessKeyEcsSecretKeyAndOthers.yml | In this Playbook, we tried to query an instance status with Alias as Ecs AccessKey, Ecs SecretKey and other parameters | Instance status should be queried | Instance status is queried successfully | Pass
8 | Verify that an instance is queried when Environment variables are set by for accesskey, secretkey and zone parameter | query_instance_statusWithEnvironmentVariableSet.yml | In this Playbook, we tried to query an instance status by setting Environment variables | Instance status should be queried | Instance status is queried successfully | Pass
9 | Verify that an instance is not queried when invalid page number is provided | query_instance_statusWithInvalidPageNumber.yml | In this Playbook, we tried to query an instance status with invalid page number parameter which is invalid test case | Instance status should not be queried | Instance status is not queried | Pass
10 | Verify that an instance is not queried when invalid page size is provided | query_instance_statusWithInvalidPageSize.yml | In this Playbook, we tried to query an instance status with invalid page size parameter which is invalid test case | Instance status should not be queried | Instance status is not queried | Pass
11 | Verify that an instance is not queried when invalid region and valid zone parameter is provided | query_instance_statusWithInvalidRegionAndValidZoneParameter.yml | In this Playbook, we tried to query an instance status with invalid region and valid zone parameter which is invalid test case | Instance status should not be queried | Instance status is not queried | Pass
12 | Verify that an instance is not queried when invalid region and zone parameter is provided | query_instance_statusWithInvalidRegionAndZoneParameter.yml | In this Playbook, we tried to query an instance status with invalid region and zone parameter which is invalid test case | Instance status should not be queried | Instance status is not queried | Pass
13 | Verify that an instance is queried with maximum page size | query_instance_statusWithMaximumPageSize.yml | In this Playbook, we tried to query an instance status with maximum page size value | Instance status should be queried | Instance status is queried successfully | Pass
14 | Verify that an instance is not queried when state parameter is not provided | query_instance_statusWithoutStateParameter.yml | In this Playbook, we tried to query an instance status without state parameter which is invalid test case | Instance status should not be queried | Instance status is not queried | Pass
15 | Verify that an instance is not queried when state parameter is not provided | query_instance_statusWithPageNumberAsString.yml | In this Playbook, we tried to query an instance status with page number as a string value which is invalid test case | Instance status should not be queried | Instance status is not queried | Pass
16 | Verify that an instance is not queried when page size is provided as a String | query_instance_statusWithPageSizeAsString.yml | In this Playbook, we tried to query an instance status with Page size as a string value which is invalid test case | Instance status should not be queried | Instance status is not queried | Pass
17 | Verify that an instance is not queried when region is considered as default parameter | query_instance_statusWithRegionAsDefaultValue.yml | In this Playbook, we tried to query an instance status with Region as default value which is invalid test case | Instance statu should not be queried | Instance status is not queried | Pass
18 | Verify that an instance is queried when valid page number is provided | query_instance_statusWithValidPageNumber.yml | In this Playbook, we tried to query an instance status with valid page number parameter | Instance status should be queried | Instance status is queried successfully | Pass
19 | Verify that an instance is queried when valid page size is provided | query_instance_statusWithValidPageSizeValue.yml | In this Playbook, we tried to query an instance status with valid page size parameter | Instance status should be queried | Instance status is queried successfully | Pass
20 | Verify that an instance is queried when valid region and zone parameter is provided | query_instance_statusWithValidRegionAndZoneParameter.yml | In this Playbook, we tried to query an instance status with valid region and zone parameter | Instance status should be queried | Instance status is queried successfully | Pass
21 | Verify that an instance is queried when zone parameter is considered as default | query_instance_statusWithZoneAsDefaultValue.yml | In this Playbook, we tried to query an instance status with zone as a default value | Instance status should be queried | Instance status is queried successfully | Pass
Modifying Instance Attributes
Test Case Id | Test Case Name | Playbook File | Description | Expected Result | Actual Result | Click2Cloud Testing Team | Aliyun Testing Team
1 | Verify that an instance's attributes are modified by setting Accesskey, Secretkey, Region parameter as Environment variables | modify_InstanceAttributeAfterSettingEnvironmentVariable.yml | In this Playbook, we tried to modify an instance attribute after setting environment variable | Instance attributes should be modified | Instance attributes are modified successfully | Pass
2 | Verify that an attributes of multiple instances are modified from the single playbook | modify_InstanceAttributeOfMulitpleInstances.yml | In this Playbook, we tried to modify attributes of multiple instances | Instance attributes should be modified | Instance attributes are modified successfully | Pass
3 | Verify that an instance's attributes are modified when Alias are provided for Accesskey, Secretkey, Acszone parameter | modify_InstanceAttributeWithAliasAsAccessKeySecretKeyAcsZone.yml | In this Playbook, we tried to modify Instance attribute with Alias AccessKey, SecretKey, AcsZone parameter | Instance attributes should be modified | Instance attributes are modified successfully | Pass
4 | Verify that an instance's attributes are modified when Alias are provided as Ecs Accesskey, Ecs SecretKey and Ecs Region Parameter | modify_InstanceAttributeWithAliasAsEcsAccessKeySecretKeyRegion.yml | In this Playbook we tried to modify Instance attribute with Alias as ECS AccessKey Ecs SecretKey Ecs Region parmeter | Instance attributes should be modified | Instance attributes are modified successfully | Pass
5 | Verify Description parameter with all the possbile scenarios | ModifyDescriptionParameter.yml | In this Playbook we tried to covere all the scenarios with Description parameter | Playbook should pass all the scenarios for Description parameter | Playbook is passing all the scenarios for Description parameter | Pass
6 | Verify HostName parameter with all the possbile scenarios | ModifyHostNameParameter.yml | In this Playbook we tried to covere all the scenarios with HostName parameter | Playbook should pass all the scenarios for HostName parameter | Playbook is passing all the scenarios for HostName parameter | Pass
7 | Verify ImageId parameter with all the possbile scenarios | ModifyImageIdParameter.yml | In this Playbook we tried to covere all the scenarios with ImageId parameter | Playbook should pass all the scenarios for ImageId parameter | Playbook is passing all the scenarios for ImageId parameter | Pass
8 | Verify InstanceName parameter with all the possbile scenarios | ModifyInstanceNameParameter.yml | In this Playbook we tried to covere all the scenarios with InstanceName parameter | Playbook should pass all the scenarios for InstanceName parameter | Playbook is passing all the scenarios for InstanceName parameter | Pass
9 | Verify Password parameter with all the possbile scenarios | ModifyPasswordParameter.yml | In this Playbook we tried to covere all the scenarios with Password parameter | Playbook should pass all the scenarios for Password parameter | Playbook is passing all the scenarios for Password parameter | Pass

## ECS Instance Parameter Testing
ECS Instance Parameter Validation
Test Case Id | Test Case Name | Playbook File | Description | Click2Cloud Testing Team | AliyunTesting Team
1 | Verify the Parameters i.e. Access Key and Secret Key | validateAccessKeyAndSecretKey.yml | In this Playbook , we tried to cover all the scenarios for the validation of Access Key and Secret Key parameter | Pass
2 | Verify the Parameters i.e. Allocate public ip | validateAllocatePublicIp.yml | In this Playbook , we tried to cover all the scenarios for the validation of Allocate public ip parameter | Pass
3 | Verify the Parameters i.e. Auto renew | validateAutoRenewParameter.yml | In this Playbook , we tried to cover all the scenarios for the validation of Auto renew parameter | Pass
4 | Verify the Parameters i.e. Count | validateCount.yml | In this Playbook , we tried to cover all the scenarios for the validation of Count parameter | Pass
5 | Verify Create instance with Mandatory parameters only | validateCreateInstanceWithMandatoryParameters.yml | In this Playbook , we tried to cover all the scenarios for the validation of Create instance with Mandatory parameters | Pass
6 | Verify the Parameters i.e. Description | validateDescription.yml | In this Playbook , we tried to cover all the scenarios for the validation of Description parameter | Pass
7 | Verify the Parameters i.e. Hostname | validateHostname.yml | In this Playbook , we tried to cover all the scenarios for the validation of Hostname parameter | Pass
8 | Verify the Parameters i.e. Ids | validateIds.yml | In this Playbook , we tried to cover all the scenarios for the validation of Ids parameter | Pass
9 | Verify the Parameters i.e. Image id | validateImageId.yml | In this Playbook , we tried to cover all the scenarios for the validation of Image id parameter | Pass
10 | Verify the Parameters i.e. Instance charge type | validateInstanceChargeType.yml | In this Playbook , we tried to cover all the scenarios for the validation of Instance charge type parameter | Pass
11 | Verify the Parameters i.e. Instance name | validateInstanceName.yml | In this Playbook , we tried to cover all the scenarios for the validation of Instance name parameter | Pass
12 | Verify the Parameters i.e. Instance tag | validateInstanceTag.yml | In this Playbook , we tried to cover all the scenarios for the validation of Instance tag parameter | Pass
13 | Verify the Parameters i.e. Instance type | validateInstanceType.yml | In this Playbook , we tried to cover all the scenarios for the validation of Instance type parameter | Pass
14 | Verify the Parameters i.e. Internet data | validateInternetData.yml | In this Playbook , we tried to cover all the scenarios for the validation of Internet data parameter | Pass
15 | Verify the Parameters i.e. Password | validatePassword.yml | In this Playbook , we tried to cover all the scenarios for the validation of Password parameter | Pass
16 | Verify the Parameters i.e. Period | validatePeriod.yml | In this Playbook , we tried to cover all the scenarios for the validation of Period parameter | Pass
17 | Verify the Parameters i.e. Region id | validateRegionId.yml | In this Playbook , we tried to cover all the scenarios for the validation of Region id parameter | Pass
18 | Verify the Parameters i.e. Security group id | validateSecurityGroupId.yml | In this Playbook , we tried to cover all the scenarios for the validation of Security Group id parameter | Pass
19 | Verify the Parameters i.e. Zone id | validateZoneID.yml | In this Playbook , we tried to cover all the scenarios for the validation of Zone id parameter | Pass
20 | Verify the Parameters i.e. VSwitch Id | validateVswitchId.yml | In this Playbook , we tried to cover all the scenarios for the validation of VSwitch Idparameter | Pass
21 | Verify the Parameters i.e. IoOptimized | validateIoOptimized.yml | In this Playbook , we tried to cover all the scenarios for the validation of IoOptimized parameter | Pass
22 | Verify the Parameters i.e. BindEip | validateBindEip.yml | In this Playbook , we tried to cover all the scenarios for the validation of BindEip parameter | Pass
23 | Verify the Parameters i.e. SystemDisk | validateSystemDisk.yml | In this Playbook , we tried to cover all the scenarios for the validation of SystemDisk parameter | Pass
24 | Verify the Parameters i.e. Volume | validateVolume.yml | In this Playbook , we tried to cover all the scenarios for the validation of Volume parameter | Pass
25 | Verify Accesskey, Secretkey, Region, Zone as Acs alias | ValidateAliasAs-Access_keySecret_keyAcs_regionAcs_zone.yml | In this Playbook, we tried to verify the instance creation with Alias as ACS Accesskey, ACS Secretkey, ACS region, ACS zone parmaeter | Pass
26 | Verify Alias for Ecs Accesskey, Ecs SecretKey, Ecs Region, Ecs Zone parmeter | ValidateAliasEcsAccessKeySecretKeyRegionZone.yml | In this Playbook, we tried to verify the instance creation with Alias as ECS Accesskey, ECS secret key, ECS region and ECS zone parameter | Pass
27 | Verify Wait and Wait-timeout parmeter | validateWaitAndWaitTimeoutParameter.yml | In this Playbook, we tried to cover all the scenarios related to wait and wait-timeout parameter | Pass

## SECURITY GROUP INTERFACES
Query Security Group
Test Case Id | Test Case Name | Playbook File | Description | Expected Result | Actual Result | Click2Cloud Testing Team | Aliyun Testing Team
1 | Verify that the security group is queried with all the mandatory parameters | query_sec_groupAllMandatoryPrameters.yml | In this Playbook, we tried to query the security group with all the mandatory parameters | Security Group should be queried | Security Group should be queried | Pass
2 | Verify that the security group is queried which is attached to an instance | query_sec_groupAttachedToAnInstance.yml | In this Playbook, we tried to query the security group attached to an instance | Security Group should be queried | Security Group should be queried | Pass
3 | Verify that the security group is not queried with the zone parameter | query_sec_groupFromZone.yml | In this Playbook, we tried to provide invalid parameter zoneid to query an instance | Security Group should not be queried | Security Group should not be queried | Pass
4 | Verify that the security group is queried which is referred by another security group | query_sec_groupWhichIsReferredByAnotherGroup.yml | In this Playbook , we tried to query the security group which is referred by another security group | Security Group should be queried | Security Group should be queried | Pass
5 | Verify that the security group is not queried with invalid access key parameter | query_sec_groupWithInvalidAccessKey.yml | In this Playbook , we tried to query the security group with invalid AccessKey parameter | Security Group should not be queried | Security Group should not be queried | Pass
6 | Verify that the security group is not queried with invalid region parameter | query_sec_groupWithInvalidRegionIdParameter.yml | In this Playbook , we tried to query the security group with invalid RegionId parameter | Security Group should not be queried | Security Group should not be queried | Pass
7 | Verify that the security group is not queried with invalid secret key parameter | query_sec_groupWithInvalidSecretKey.yml | In this Playbook , we tried to query the security group with invalid SecretKey parameter | Security Group should not be queried | Security Group should not be queried | Pass
8 | Verify that the security group is not queried with invalid state parameter | query_sec_groupWithInvalidStateParameter.yml | In this Playbook , we tried to query the security group with invalid State parameter | Security Group should not be queried | Security Group should not be queried | Pass
9 | Verify that the security group is not queried with invalid Vpcid parameter | query_sec_groupWithInvalidVpcId.yml | In this Playbook , we tried to query the security group with invalid VpcId parameter | Security Group should not be queried | Security Group should not be queried | Pass
10 | Verify that the security group is not queried without regionid parameter | query_sec_groupWithoutRegionIdParameter.yml | In this Playbook, we tried to query the security group without RegionId parameter | Security Group should not be queried | Security Group should not be queried | Pass
11 | Verify that the security group is not queried without state parameter | query_sec_groupWithoutStateParameter.yml | In this Playbook, we tried to query the security group without State parameter | Security Group should not be queried | Security Group should not be queried | Pass
12 | Verify that the security group is queried with valid Vpcid parameter | query_sec_groupWithValidVpcId.yml | In this Playbook, we tried to query the security group with valid VpcId | Security Group should not be queried | Security Group should not be queried | Pass
Delete Security Group
Test Case Id | Test Case Name | Playbook File | Description | Expected Result | Actual Result | Click2Cloud Testing Team | Aliyun Testing Team
13 | Verify that the security group is not deleted when attached to the VPC instance | delete_sec_groupAttachedToVPCInstance.yml | In this Playbook , we tried to delete the security group attached to Vpc instance, which is invalid test case | Security Group should not be deleted | Security Group should be queried | Pass
14 | Verify that the security group is not deleted when attached to the instance | delete_sec_groupWhenAttachedWithAnInstance.yml | In this Playbook , we tried to delete the security group attached to Classic instance, which is invalid test case | Security Group should not be deleted | Security Group should be queried | Pass
15 | Verify that the security group is not deleted when referred by another secruity group | delete_sec_groupWhenReferencedByaRuleOfOtherGroup.yml | In this Playbook , we tried to delete the security group referred by another group, which is invalid test case | Security Group should not be deleted | Security Group should not be queried | Pass
16 | Verify that the security group is deleted with all the mandatory parameters | delete_sec_groupWithAllMandatoryParameters.yml | In this Playbook , we tried to delte the security group with all the mandatory parameters | Security Group should be deleted | Security Group should be queried | Pass
17 | Verify that the security group is not deleted with invalid groupid parameter | delete_sec_groupWithInvalidGroupIdParameter.yml | In this Playbook, we tried to delete the security group with invalid groupid parameter | Security Group should not be deleted | Security Group should not be queried | Pass
18 | Verify that the security group is not deleted with invalid regionid parameter | delete_sec_groupWithInvalidRegionIdParameter.yml | In this Playbook, we tried to delete the security group with invalid regionid parameter | Security Group should not be deleted | Security Group should not be queried | Pass
19 | Verify that the security group is not deleted with invalid state parameter | delete_sec_groupWithInvalidStateParameter.yml | In this Playbook, we tried to delete the security group with invalid state parameter | Security Group should not be deleted | Security Group should not be queried | Pass
20 | Verify that the security group is deleted when multiple group ids are provided | delete_sec_groupWithMulitpleGroupIdsparameter.yml | In this Playbook, we tried to delete the multiple security groups | Security Group should be deleted | Security Group should not be queried | Pass
21 | Verify that the security group is not deleted when groupid is not provided | delete_sec_groupWithoutGroupIdParameter.yml | In this Playbook, we tried to delte the security group without groupid parameter, which is invalid test case | Security Group should not be deleted | Security Group should not be queried | Pass
22 | Verify that the security group is not deleted when regionid is not provided | delete_sec_groupWithoutRegionIdParameter.yml | In this Playbook, we tried to delte the security group without regionid parameter, which is invalid test case | Security Group should not be deleted | Security Group should not be queried | Pass
23 | Verify that the security group is not deleted when state parameter is not provided | delete_sec_groupWithoutStateParameter.yml | In this Playbook, we tried to delte the security group without state parameter, which is invalid test case | Security Group should not be deleted | Security Group should not be queried | Pass
[5 empty] | Security Group should not be queried | Pass
Create Security Group
Test Case Id | Test Case Name | Playbook File | Description | Expected Result | Actual Result | Click2Cloud Testing Team | Aliyun Testing Team
24 | Check all the Scenarios Security Group Name Validation | create_sec_group_SecurityGroupNameValidation.yml | In these playbooks , we tried to cover all parameter validation and Basic Scenarios for creating Security Group |  |  | Pass
25 | Verify that the security group is not created with invalid region Id | create_sec_group_WithInvalidRegionId.yml | In these playbooks , we tried to cover all parameter validation and Basic Scenarios for creating Security Group | positiveand Negative scenarios should be handled based on tasks | positive and Negative scenarios is handled based on tasks | Pass
26 | Check all the Scenarios for Security Group Description | create_sec_group_WithInvalidSecGroupDescName.yml | In these playbooks , we tried to cover all parameter validation and Basic Scenarios for creating Security Group | Security Group should not be created | Security Group is not created | Pass
27 | Verify that the security group is not created with invalid vpc Id | create_sec_group_WithInvalidVpcId.yml | In these playbooks , we tried to cover all parameter validation and Basic Scenarios for creating Security Group | Security Group should not be created | Security Group is not created | Pass
28 | Verify that the security group is not created with missing Parameter Region Id | create_sec_group_WithMissingParameterRegionId.yml | In these playbooks , we tried to cover all parameter validation and Basic Scenarios for creating Security Group | Security Group should not be created | Security Group is not created | Pass
29 | Verify that the security group is not created with missing Parameter Security Group name | create_sec_group_withSecGroupNameMissingParameter.yml | In these playbooks , we tried to cover all parameter validation and Basic Scenarios for creating Security Group | Security Group should not be created | Security Group is not created | Pass
30 | Verify that the security group is attached to valid vpc Id | create_sec_groupAndAttachedItToVPC.yml | In these playbooks , we tried to cover all parameter validation and Basic Scenarios for creating Security Group | Security Group should be attached to vpc | Security Group is attached to vpc | Pass
31 | Verify that the security group is created with all mandatory Parameter | create_sec_groupWithAllMandatoryParameters.yml | In these playbooks , we tried to cover all parameter validation and Basic Scenarios for creating Security Group | Security Group should be created | Security Group is created | Pass
32 | Verify that the security group is created with defined Internet Inbound/Outbound Rules | create_sec_group_WithBothInternetInboundOutboundRules.yml | In these playbooks , we tried to cover all parameter validation and Basic Scenarios for creating Security Group | Security Group should be created with Defined Internet Inbound/Outbound Rules | Security Group is created with Defined Internet Inbound/Outbound Rules | Pass
33 | Verify that the security group is created with defined Intranet Inbound/Outbound Rules | create_sec_group_WithBothIntranetInboundOutboundRules.yml | In these playbooks , we tried to cover all parameter validation and Basic Scenarios for creating Security Group | Security Group should be created with Defined Intranet Inbound/Outbound Rules | Security Group is created with Defined Intranet Inbound/Outbound Rules | Pass
34 | Verify that the security group is created with defined Internet Inbound Rules | create_sec_group_WithInternetInboundRules.yml | In these playbooks , we tried to cover all parameter validation and Basic Scenarios for creating Security Group | Security Group should be created with Defined Internet Inbound Rules | Security Group is created with Defined Internet Inbound Rules | Pass
35 | Verify that the security group is created with defined Internet Outbound Rules | create_sec_group_WithInternetOutboundRules.yml | In these playbooks , we tried to cover all parameter validation and Basic Scenarios for creating Security Group | Security Group should be created with Defined Internet OutBound Rules | Security Group is created with Defined Internet OutBound Rules | Pass
36 | Verify that the security group is created with defined Intranet Inbound Rules | create_sec_group_WithIntranetInboundRules.yml | In these playbooks , we tried to cover all parameter validation and Basic Scenarios for creating Security Group | Security Group should be created with Defined Internet Inbound Rules | Security Group is created with Defined Intranet Inbound Rules | Pass
37 | Verify that the security group is created with defined Intranet Outbound Rules | create_sec_group_WithIntranetOutboundRules.yml | In these playbooks , we tried to cover all parameter validation and Basic Scenarios for creating Security Group | Security Group should be created with Defined Internet OutBound Rules | Security Group is created with Defined Intranet OutBound Rules | Pass